## Sheet1
[Revise Portlet Layout Manager protocol for user test | 2
[Revise questionnaires for Portlet Layout Manager user test | 1
[Recruit users for Portlet Layout Manager user test | 2
Keyboard Interactions | 2
Integration with new uPortal skin | 1
Complete Contextual Inquiry Guides \\ | 1
Contextual Inquiry - Toronto faculty 1 (2 UX team members) \\ | 1.25
Contextual Inquiry - Toronto faculty 2 (2 UX team members) | 1.25
Contextual Inquiry - Toronto TA 1 (2 UX team members) | 1.25
Contextual Inquiry - Berkeley faculty 1 (2 UX team members) | 1.25
Contextual Inquiry - Berkeley faculty 2 (2 UX team members) | 1.25
Contextual Inquiry - Berkeley faculty 3 (2 UX team members) | 1.25
Contextual Inquiry - Berkeley TA 1 (2 UX team members) | 1.25
Design Patterns - Work w/Oracle | 1
Design Patterns - UX review of OSDPL | 1
Design Patterns - Enter Fluid Design Patterns into OSDPL | 0.25
Design Patterns - Review Sakai Design Patterns for wording from other libraries & add any needed attribution | 0.5
Design Patterns - Create Open Source Design Patterns working group charter (address how the different communities will work together on patterns) | 0.5
Design Patterns - Invite folks from mailing lists (sakai-ui, fluid-work, jasig-ue) to OSDP working group | 0.25
Design Patterns - Hold first & subsequent weekly OSDP working group meetings, review charter, allocate tasks, choose roles, plan & take next steps | 2.25
Design Patterns - Determine copyright strategy/permission from Yahoo\!, Google w/Sheila | 0.5
Design Patterns - Can we use current Sakai design pattern screenshots? What do we do if not? | 0.5
Design Patterns - Help Erin with design pattern for Paging \\ | 0.5
Design Patterns - Create OSDP Library Home page | 0.25
Kuali - Interviews | 1.5
Kuali - Maintain contact with the Kuali UX folks and offer UX advice when needed | 0.25
27